## Summary
ShareShuffle Product Backlog & Rebuild Notes
Created from 2026-06-16 handoff and current planning conversation. Use this as the living map for features, decisions, user stories, and ideas waiting until Chrome review completes.
North Star | Send the thing you meant to send. | Backlog Snapshot | Count
Product thesis | Traditional sharing moves URLs. ShareShuffle moves recommendations. | Total items | 45
Current safety mode | Keep extension package stable while Chrome review is pending; hosted/web patches are safer. | Built / live-ish | 24
Cost strategy | No LLM API fees for now; prefer browser DOM, metadata, explicit user choices, and Firebase hosting/functions. | In progress | 4
Scraping strategy | Avoid server-side scraping, especially Amazon search pages. Rescue the user’s current page instead. | Waiting / backlog / idea | 11
Current hosted static build | 2026.06.16-share-rescue-web-copy-30 | P0 | 16
Current function build | 2026.06.13-chrome-affiliate-disclosure-29 | P1 | 16
Main domains | shareshuffle.com, shfl.me | P2 | 11
Firebase project | shareshuffle-c7f96 | P3 | 2
Local repo | /Users/richwilliams/Documents/GitHub/shareshuffle.github.io | Snapshot note | Counts are static as of 2026-06-16; filter Backlog for live planning.
Patch 40 Update
Build | 2026.06.17-no-blank-fallback-40
Core fix | Placeholder-card state prevents blank/white image boxes and stops uploading fallback tiles as product images.
Reports | reports/SHARESHUFFLE_PATCH_40_REPORT.md and reports/SHARESHUFFLE_NEW_CHAT_HANDOFF_20260617.md
Next | Verify a new Guitar Center share; then consider Improve image after share creation.

## Backlog
ID | Epic | Feature / User Story | User Story | Why it matters | Status | Priority | Surface | Release target | Complexity | Cost/Risk | Acceptance criteria | Notes
SS-001 | Chrome approval | Affiliate disclosure compliance | As a Chrome reviewer/user, I need ShareShuffle to clearly disclose affiliate links before I create/share links. | Gets extension approved; builds trust; avoids misleading monetization. | In review | P0 | Chrome extension | 0.1.1 | S | Low | Manifest/Store/popup all disclose affiliate programs; disclosure appears before share creation. | Do not alter until Chrome review returns.
SS-002 | Affiliate links | Amazon affiliate tag preservation | As a creator, I want Amazon product URLs to include ShareShuffle's affiliate tag when eligible. | Core referral revenue while staying honest and compliant. | Built | P0 | Functions + web | Live | M | Medium | Amazon outbound URL includes tag=shareshuffle-20 unless an existing Amazon tag is already present. | Never overwrite existing tags.
SS-003 | Affiliate links | Walmart Impact wrapping | As a creator, I want Walmart links wrapped through the configured Impact affiliate URL when eligible. | Adds non-Amazon revenue support. | Built | P0 | Functions + web | Live | M | Medium | Walmart destination wraps through goto.walmart.com with encoded destination; existing Impact links are not double-wrapped. | Keep readable button label as Walmart/View Store.
SS-004 | Link safety | Reject hosted ShareShuffle URLs as store destinations | As a recipient, I need View Store buttons to go to the merchant, not loop back into ShareShuffle. | Prevents confusing loops and protects trust. | Built | P0 | Functions + web | Live | S | Low | Store URL chooser rejects shareshuffle.com, shfl.me, shelfmix, firebase/web.app as merchant destinations. | Prefer originalUrl/storeUrl/productUrl/merchantUrl before url.
SS-005 | App stability | Server-backed shelf data | As a visitor, I want shelf pages to load reliably without browser Firebase module failures. | Fixed stuck Loading pages; reduces frontend fragility. | Built | P0 | Functions + shelf.html | Live | M | Low | /shelfData?s=bass-gear and /shelfData?u=rich&s=bass-gear return usable JSON; shelf.html renders via fetch. | Must keep no-user shelfSlug route working for extension review/legacy shares.
SS-006 | App stability | Server-backed share data | As a visitor, I want individual share pages to load reliably. | Fixed stuck Loading pages; improves unfurl and landing reliability. | Built | P0 | Functions + share.html | Live | M | Low | /shareData?id=abc12 returns title, note, image, merchant, store URL; share.html renders via fetch. | Avoid browser Firebase import failures.
SS-007 | Analytics | Share click tracking | As the product owner, I want outbound share/store clicks tracked. | Shows whether recommendations convert into meaningful actions. | Built | P1 | Functions | Live | S | Low | /trackShareClick?id=abc12 increments safely without breaking outbound navigation. | Keep privacy-light; no creepy tracking.
SS-008 | Image quality | Image Rescue / pick best image | As a creator, I want to choose the best image when a product page offers multiple image candidates. | Made shares feel much more polished; user control without LLM cost. | Built | P0 | Extension/web flow | Live-ish | M | Low | UI shows image options, selected image persists on share, bad tiny images avoided when possible. | Pattern should inspire Search Result Rescue.
SS-009 | Image quality | Generated rescue/card image route | As a recipient/social platform, I want a reliable card image even if merchant image is bad. | Improves iMessage/social previews; prevents blank white cards. | In progress | P0 | Functions/OG | Next hosted patch | M | Medium | shfl.me/share routes expose absolute og:image; /i-{id} or /c-{id} returns real image bytes with correct content type. | Current iMessage preview works but can show blank image.
SS-010 | Share previews | OG metadata hardening | As a recipient, I want the share preview to show title, source, image, and destination clearly. | First impression in iMessage/social; critical to trust. | In progress | P0 | Functions + routes | Next hosted patch | M | Medium | shfl.me links include title, description, absolute image URL, image width/height/type, and redirect cleanly. | Do not overreact to one platform's inconsistent unfurling.
SS-011 | Share Rescue | Search-result URL detection in web app | As a user pasting a link, I want ShareShuffle to warn me if I pasted search results instead of a specific thing. | Prevents the YouTube/Amazon mistake; makes app feel helpful. | Built | P1 | Web app /app | Patch 30 | S | Low | Pasting Amazon/YouTube/Google/Walmart/Target/eBay/Best Buy search URLs shows friendly guidance and does not block saving. | Hosted-only; no extension package change.
SS-012 | Share Rescue | Search Result Rescue chooser in extension | As a user on Amazon search results, I want to pick the product I meant to share from visible results. | Most useful next extension feature after approval; turns messy links into recommendations. | Waiting | P1 | Chrome extension | 0.1.2 | M | Low/Medium | On supported search pages, popup lists first visible result cards with title/image/url; choosing one fills popup with the real product. | Use DOM already loaded by browser; no server scrape.
SS-013 | Share Rescue | YouTube search-result chooser | As a user on YouTube search results, I want to pick the video I meant to share. | Perfect non-commerce proof that ShareShuffle fixes broken sharing generally. | Idea | P2 | Chrome extension | Later | M | Low/Medium | Detect /results?search_query; show visible video results; selected video becomes the shared URL. | No affiliate angle; supports product story.
SS-014 | Share Rescue | Blue hover-box page selection mode | As a user, I want to click the exact product/video/card on the page that I mean to share. | Demo magic; feels like 'rescued' sharing. | Idea | P2 | Chrome extension content script | Later | L | Medium | User enters pick mode; hover outlines eligible share items; click captures title/image/url; Esc cancels. | Sexy but more complex and more review-sensitive.
SS-015 | Share Rescue | Warn-only fallback | As a user, I still want help even if ShareShuffle cannot extract choices. | Tiny, sustainable rescue that avoids bad shares. | Built/extend | P1 | Web + extension | 0.1.2 | S | Low | For search/category pages, display: 'This looks like search results. Open the exact item first, or save the search if that is what you mean.' | Do not scold. Rescue tone.
SS-016 | Web app | Homepage feature language refresh | As a first-time visitor, I want to understand that ShareShuffle sends recommendations, not just links. | Positions product beyond affiliate tagging. | Built | P1 | Home page | Patch 30 | S | Low | Homepage adds Share Rescue, Image Rescue, message-ready sharing, affiliate-aware language without removing existing sections. | Tagline: Send the thing you meant to send.
SS-017 | Web app | Mobile creator / paste flow | As a phone user, I want to paste a product link, add note/shelf, and send it again. | Supports non-extension use cases and PWA direction. | Built/ongoing | P1 | /app | Live | M | Low | App has product URL input, paste button, preview filled message, note/shelf fields, and last share state. | Current UI shows search-result warning.
SS-018 | PWA | Add to Home Screen messaging | As a mobile user, I want ShareShuffle to behave like an app without installing from an app store. | Important low-cost mobile path. | Built/ongoing | P2 | /app PWA | Live | S | Low | Add to Home Screen CTA present; app remains usable as standalone PWA. | Later: share target support.
SS-019 | PWA | Native Web Share outbound | As a user, I want one Share button that opens the iOS/Android share sheet. | More convenient than copy/paste; no Xcode needed. | Backlog | P1 | Web/PWA | Soon | M | Low | Use navigator.share where available; keep Copy URL and Copy Text separate; fallback to SMS/email. | Desired: Copy URL = short link; Copy Text = full 'Shared via Shuffle' message.
SS-020 | PWA | PWA Share Target inbound | As a phone user, I want to send a product URL to ShareShuffle from the phone share sheet. | Transforms mobile capture workflow. | Backlog | P2 | PWA manifest/service worker | Later | L | Medium | ShareShuffle appears as a share target; inbound URL pre-fills creator flow. | Requires careful testing across iOS/Android.
SS-021 | Shelf pages | Rich's Bass Gear demo shelf | As a prospective user/reviewer, I want a polished real-world shelf demo. | Demo credibility; bass gear niche is authentic. | In progress | P0 | shelf.html/data | Now | M | Low | Bass gear shelf loads, cards look polished, duplicates cleaned, affiliate buttons correct, public route works. | Use Rich's bass products and personal notes.
SS-022 | Shelf design | Stable editorial card rails | As a visitor, I want product cards to look premium but not chaotic. | Preserves 'hot zoom' look while avoiding giant unpredictable images. | Built/ongoing | P1 | shelf.html | Live | M | Low | Fixed crop window, consistent card body height, clamped title/note, stable button row, intentional placeholder. | Keep moodboard energy.
SS-023 | Shelves | No-user legacy shelf route support | As a legacy extension share, I need shelves created without handleSlug to still render. | Protects Chrome review and old links. | Built | P0 | shelfData/shelf.html | Live | S | Low | shelf.html?s=bass-gear works even without u=rich. | Do not break while adding username routing.
SS-024 | Routing | Username routing | As a creator, I want clean public shelf/profile routes like shfl.me/@rich/bass-gear/abc12. | Better personal sharing and brand value. | In progress | P1 | Functions/router | Soon | L | Medium | Support shfl.me/@rich/shelf/share style routes; canonical redirects avoid duplicate/confusing pages. | Current link in test: shfl.me/@rich/bass-gear/3ycrk.
SS-025 | Routing | Short-link route cleanup | As a recipient, I want shfl.me links to land cleanly on the right content. | Core user experience. | Built/ongoing | P0 | Functions/router | Live | M | Medium | shfl.me/{id} resolves; old shfl.me/share.html?id= redirects to shareshuffle.com/share.html?id=. | Do not let short-link domain serve old app pages incorrectly.
SS-026 | Admin | Clean up duplicate/old test shares | As product owner, I want the demo shelf to avoid duplicates and junk test data. | Polish for reviewers and friends. | Backlog | P1 | Admin/data | Soon | S | Low | Admin can identify duplicate normalized title/url/image; old test entries hidden/deleted. | Do carefully; preserve useful test cases.
SS-027 | Admin | Minimal password-protected admin/dashboard | As product owner, I want basic control pages without exposing management actions publicly. | Operational hygiene. | Built/ongoing | P2 | admin/dashboard | Live-ish | M | Medium | Admin titles one-line ellipsis; simple password gating; no sensitive secrets in client. | Not a full auth system yet.
SS-028 | Firestore | Rules in repo / GitHub-driven deploy | As product owner, I want Firebase rules versioned with the site. | Safer deployments; easier rebuild. | Backlog | P1 | Repo/deploy | Soon | M | Low | firestore.rules is committed; deploy command deploys hosting, functions, firestore:rules. | CLI EACCES issue noted on Mac.
SS-029 | Waitlist | Firebase waitlist capture | As an interested visitor, I want to join a waitlist and share what kind of recommendations I care about. | Captures demand before full auth. | Built | P2 | Home/investor Firebase | Live | M | Low | waitlist collection captures email, firstName, source, interestType, favoriteRecommendation, createdAt=request.time, pageUrl. | Later: confirmation email.
SS-030 | Messaging | Message-ready share text | As a sender, I want a share message that explains the recommendation, not just a link. | Makes recommendations human and clear. | Built/ongoing | P1 | Web/extension | Live-ish | M | Low | Text includes creator handle/name, personal note, product title, and shfl.me link. | Example shown in iMessage: 'rich shared via Shuffle: This is my lottery bass…'
SS-031 | Messaging | SMS fallback / Message button | As a user, I want a quick way to send shares through Messages/SMS. | Convenience on mobile and desktop. | Backlog | P2 | Web/extension | Soon | S | Low | Message button opens sms: fallback with prefilled message where supported. | Keep separate from native Share.
SS-032 | Messaging | Email share fallback | As a user, I want to send a recommendation by email. | Basic universal sharing path. | Backlog | P3 | Web/extension | Later | S | Low | Email button opens mailto with subject/body including note/title/link. | Less urgent than SMS/native share.
SS-033 | Merchant UX | Dynamic merchant button labels | As a recipient, I want the button to say the actual merchant, not always Amazon. | Avoids weird Walmart/Amazon mismatch. | Built/ongoing | P0 | share/shelf cards | Live | S | Low | Button label changes by merchant: View on Amazon, View at Walmart, View Store, etc. | Earlier bug showed Amazon for Walmart.
SS-034 | Merchant UX | Supported merchant badge | As a user browsing, I want to know when ShareShuffle supports the current site. | Makes extension feel present but unobtrusive. | Built | P2 | Chrome extension | 0.1.1 | S | Low | Extension badge uses plus sign + with tooltip 'ShareShuffle supports this site.' | Supported domains: Amazon, Walmart, Target, Best Buy, eBay.
SS-035 | Security | Title/note link safety | As a recipient, I do not want malicious/clickable junk in titles/notes. | Prevents accidental linkification/injection and confusing previews. | Backlog/ongoing | P1 | Web/rendering | Soon | M | Medium | URL characters in user text are escaped/sanitized; Amazon.com in title does not become clickable. | Use escapeHtml and careful text rendering.
SS-036 | Brand | Simplify public brand around ShareShuffle + shfl.me | As a visitor, I want one clear brand instead of ShelfMix confusion. | Cleaner launch/reviewer experience. | Decision pending | P2 | Brand/home/shelves | Soon | S | Low | Public pages primarily say ShareShuffle; ShelfMix can remain internal/collection wording. | ShelfMix.com owned but not replacing ShareShuffle.
SS-037 | Brand | S-node logo/icon system | As a user, I want the app icon to feel recognizable and polished. | Brand trust and home screen presence. | Built/ongoing | P2 | Assets | Live | M | Low | Baby blue #EEF6FF icon background; transparent favicon small; dark-mode favicon white-on-black. | Avoid gooey S, avoid circle, include padding.
SS-038 | Build ops | Build status page | As product owner, I want to confirm static and function builds after deploy. | Prevents guessing after patches. | Built | P1 | status.html/_build | Live | S | Low | Status page shows static build, function build, smoke test links. | Next: clarify expected static vs expected function build.
SS-039 | Build ops | Folder-based patch install command | As Rich on Mac, I want patch commands that work when downloads auto-unzip. | Reduces friction and mistakes. | Built process | P0 | Workflow | Ongoing | S | Low | Use ditto folder command first, then npm --prefix functions install, firebase deploy. | Avoid only zip extraction instructions.
SS-040 | Chrome review | Do not turn compliance resubmission into feature release | As product owner, I want to avoid re-triggering review risk with unrelated changes. | Maximizes approval odds. | Active constraint | P0 | Extension release mgmt | Now | S | Low | No new extension package unless Chrome asks/rejects; hosted changes okay if not breaking review routes. | 0.1.2 waits after approval.
SS-041 | Roadmap | Affiliate-aware, not affiliate-first positioning | As a user, I want to feel like ShareShuffle improves sharing, not like it hijacks links. | Trust + product differentiation. | Built language | P1 | Home/copy | Patch 30 | S | Low | Copy says recommendations first; affiliate links support service at no extra cost; compliant disclosure remains visible. | Important for Chrome and users.
SS-042 | Roadmap | Universal 'thing you meant to send' thesis | As a stakeholder, I want a clear north star for product decisions. | Guides features beyond commerce. | Accepted | P1 | Strategy | Ongoing | S | Low | North-star tagline is used in planning/copy: 'Send the thing you meant to send.' | Related: 'Traditional sharing moves URLs. ShareShuffle moves recommendations.'
SS-043 | Future | Reverb/music gear merchant support | As a musician, I want ShareShuffle to understand music gear marketplaces. | Authentic niche expansion for bass demo and affiliate/recommendation use. | Idea | P2 | Extension/web | Later | M | Medium | Detect Reverb product pages/search pages; merchant button/metadata work; possible affiliate program researched later. | Fits Rich's bass gear audience.
SS-044 | Future | AI/LLM features held until affordable | As product owner, I want to avoid recurring LLM API fees until revenue supports them. | Keeps costs near zero. | Decision | P3 | Strategy | Later | L | High cost | No LLM-dependent features in near-term roadmap. | Use browser DOM, metadata, explicit user choices instead.
SS-045 | Future | No server scraping strategy | As product owner, I want to avoid bot/scraping risk from retailers. | Reduces blocks, dog pages, compliance worries. | Decision | P0 | Architecture | Ongoing | S | Low | Search/result rescue uses extension DOM where possible; web app warns only; backend does not crawl Amazon search pages. | Amazon dog pages validate this caution.
SS-046 | Image quality | No blank fallback card state | As a sender, I want blocked-image shares to still look intentional, so my message preview never shows a blank box or 'Image not added yet.' | Blank image boxes killed the magic in iMessage for Guitar Center/Walmart-style links. | Done | P0 | Web app + Functions | Patch 40 | M | Low | If no product image can be cached, share uses imageStatus=placeholder-card; /c-{id} renders a clean fallback panel; /i-{id} returns a designed square fallback. | Patch 40 treats the fallback as a final-card state, not an uploaded image.
SS-047 | Image quality | Placeholder is not a product image | As product owner, I want the app to distinguish a user-uploaded product photo from a ShareShuffle fallback card. | Avoids misleading uploaded-photo copy and prevents a title-card from being placed inside the product image slot. | Done | P0 | Web app create flow | Patch 40 | S | Low | Choosing ShareShuffle card sets selectedImageSource=placeholder-card, does not create a data URL product image upload, and skips image caching. | Closes the white-box failure loop from patches 36-38.
SS-048 | Image quality | Improve image after share creation | As a sender, I want to improve a fallback image after the share is already created, so the share completes quickly but I can still make it prettier. | Image rescue can be slow or unreliable; share creation should not feel frozen. | Backlog | P1 | Web app | Post Patch 40 | M | Low | If imageStatus=placeholder-card, Last Share Ready shows an Improve image action; choosing a backup updates cache and imageVersion. | Keeps the Don't Make Me Think flow fast while preserving polish.
SS-049 | Image quality | Image rescue progress states | As a user, I want clear progress messages while ShareShuffle searches/caches images, so I know the app is working and not frozen. | Long create time feels broken even when it completes. | Backlog | P1 | Web app UX | Post Patch 40 | S | Low | Progress states distinguish looking for backup images, saving image, falling back to card, and share created. | Should not block creation beyond a short timeout.

## Copy & Language
Category | Line / Copy | Where to use | Notes
Tagline | Send the thing you meant to send. | Home hero, Chrome listing, pitch | Strongest north-star line.
Thesis | Traditional sharing moves URLs. ShareShuffle moves recommendations. | Homepage/investor | Explains why this is bigger than short links.
Feature name | Share Rescue | Internal + possibly public feature heading | Umbrella for search/image/preview/link rescue.
Feature name | Search Result Rescue | Feature card | Detects search pages and helps user share the exact thing.
Feature name | Image Rescue | Feature card | Pick best image / avoid bad thumbnails.
Feature name | Preview Rescue | Feature card | Generate reliable social/iMessage preview cards.
UX line | This looks like search results. Which one did you mean? | Extension chooser | Warm; not scolding.
UX line | I found a few things on this page. Pick what you meant to share. | Extension chooser | Feels rescued.
UX line | ShareShuffle works best when you share the exact product you mean. | Web app paste warning | Helpful guidance.
UX line | You can still save this search if the search itself is what you mean to recommend. | Web app paste warning | Does not block user.
Commerce positioning | Affiliate-aware, not affiliate-first. | Internal/pitch | Keeps trust front and center.
Commerce disclosure | ShareShuffle may earn from qualifying purchases at no additional cost to you. | Disclosure/UI | Compliance-safe wording.
Feature line | From messy link to clear recommendation. | Homepage | Compact benefit.
Feature line | Pick the best image, add your note, and send a clean shfl.me link. | Homepage/app | Describes current value.
Chrome explanation | We updated the Chrome Web Store description and extension popup UI to prominently disclose affiliate usage before users create a share link. | Chrome appeal/reply | Use if reviewer asks what changed.
Tone rule | Do not make the user feel corrected. Make them feel rescued. | UX principle | Very Don't Make Me Think.

## Build & Routes
Area | Route / Command | Purpose | Expected / Notes
Build check | curl -s https://shareshuffle.com/_build | Check public app build | Static patch 30 may differ from function build 29.
Build check | curl -s https://shfl.me/_build | Check short domain function build | Function build currently 2026.06.13-chrome-affiliate-disclosure-29.
App | https://shareshuffle.com/app/ | Mobile/web creator paste flow | Search Result Rescue warning appears for search URLs.
Home | https://shareshuffle.com/ | Homepage copy/positioning | Should include new Share Rescue/tagline features without removing existing content.
Share data | https://shareshuffle.com/shareData?id=zhcaa | Server JSON for share page | Verify affiliate-safe store URL/image.
Share page | https://shareshuffle.com/share.html?id=zhcaa | Canonical share landing page | Should render from server data.
Short share | https://shfl.me/zhcaa | Short link redirect/render | Must work for social previews.
Shelf data | https://shareshuffle.com/shelfData?s=bass-gear | Legacy/no-user shelf JSON | Must keep working for extension/review.
Shelf page | https://shareshuffle.com/shelf.html?s=bass-gear | Legacy/no-user shelf page | Must render bass gear shelf.
Shelf page | https://shareshuffle.com/shelf.html?u=rich&s=bass-gear | User shelf page | Preferred public shelf route for Rich.
Test paste URL | https://www.amazon.com/s?k=Precision+Bass&crid=2KD27AZZCNI32&sprefix=precision+bass%2Caps%2C171&ref=nb_sb_noss_1 | Search Result Rescue test input | Should warn: Amazon search results.
Patch install | ditto "/Users/richwilliams/Downloads/PATCH-FOLDER/shareshuffle.github.io" "/Users/richwilliams/Documents/GitHub/shareshuffle.github.io" | Mac auto-unzip friendly patch install | Use folder-based ditto first.
Deploy | cd "/Users/richwilliams/Documents/GitHub/shareshuffle.github.io" && npm --prefix functions install && npx firebase-tools@latest deploy --only hosting,functions,firestore:rules | Deploy all core Firebase assets | Avoid extension package changes during review.

## Risks & Decisions
Decision / Risk | Current stance | Why | Trigger to revisit
LLM features | Hold | No LLM API fees until revenue/support exists. | Revenue, grants, or very clear ROI.
Server scraping Amazon/search pages | Avoid | Bot/dog-page/blocking/compliance risk; brittle. | Only if official API or user-authorized safe method exists.
Extension changes while in review | Avoid | Compliance-only resubmission is safest. | Chrome rejects and asks for changes, or approval completes.
ShelfMix public brand | De-emphasize for now | ShareShuffle + shfl.me is clearer during launch. | When shelf product identity needs separate brand.
Social unfurl consistency | Improve but don't obsess | iMessage/social previews are inconsistent by platform. | Repeated failures after OG hardening.
Blue hover selection mode | Later | High UX wow, but extension/content-script complexity and review sensitivity. | After chooser works and extension approval is stable.
Affiliate links | Compliant and transparent | Revenue engine, but must never feel deceptive. | Review feedback or user confusion.
Firestore/browser Firebase in public pages | Prefer server fetch endpoints | Avoid module/loading fragility on public routes. | Auth/user-owned write workflows mature.

## Reports
Report | Path | Purpose | Status
Patch 40 Report | reports/SHARESHUFFLE_PATCH_40_REPORT.md | Documents no-blank fallback decision, implementation, acceptance criteria, and test plan. | Added
New Chat Handoff | reports/SHARESHUFFLE_NEW_CHAT_HANDOFF_20260617.md | Gives the next chat the project state, Chrome review freeze, Image Rescue history, and next steps. | Added